Internal PLAN of QA/QC activities for national pollutant inventories for 2023

|  | Activity name | Responsible | Control | Deadline | Record |
| --- | --- | --- | --- | --- | --- |
| 1. | Submission of emission balance results for emission inventories by sector | Sectoral experts | Quality manager Coordinator | 15.1.2023 | Inventory of emissions in NFR 14 categorizations for the sector and for the inventory year 2021 |
| 2. | Evaluation of the 2023 improvement plan | Sectoral experts Coordinator | Quality manager | 15.2.2023 | Improvement plan for 2023 for each sector |
| 3. | Reporting of the national inventory for all sectors to EC and UNECE | Coordinator | Quality manager SAŽP | 15.2.2023 | Electronic confirmation for the MoE and SAŽP on timely reporting of national inventories |
| 4. | Assigning responsibilities to team members, incorporating updates for individual sectors | Sectoral experts | Coordinator Quality manager | 28.2.2023 | Description of work activity |
| 5. | Recalculations and correction of erroneous data | Sectoral experts | Quality manager Coordinator | 22.2.2023 | Evaluation of control |
| 6. | Analysis of key categories - trend and level assessment | Coordinator | Quality manager Sektoroví experti | 22.2.2023 | Resulting evaluation of key categories |
| 7. | Submission of sectoral reports | Sectoral experts | Quality manager Coordinator | 1.3.2023 | Sectoral reports |
| 8. | Compilation and reporting of a complete national inventory report | Coordinator | Quality manager SAŽP | 15.3.2023 | Informative inventory report on the national inventory for the year 2021 |
| 9. | In-depth review of inventory under CLRTAP and NECD | Sectoral experts Coordinator | Coordinator | máj - jún | Draft review report |
| 10. | In-depth review of the inventory report under NECD | Sectoral experts Coordinator Quality manager | Technical team of experts | November 2023 | Final report from the review process for 2023 |
| 11. | Preparation of the improvement plan for 2024 | Sectoral experts Coordinator | Quality manager | September 2023 | Improvement plan for 2024 for each sector according to recommendations from the review |
| 12. | Coordination meeting - meeting of experts Program: evaluation of the results and conclusions of the emission inventory control, submission of a proposal for improvement for the current year, development of an improvement plan for IIR 2022 | Sectoral experts Coordinator | Quality manager | September 2023 November 2023 | Minutes of the meeting |
| 13. | Reporting and publication of AEA emission accounts | Sectoral experts Coordinator | Quality manager | September 2023 | Reporting questionnaire, Quality report |

|  | name | date | signature |
| --- | --- | --- | --- |
| Prepared by: | Mgr. Lenka Zetochová |  |  |
| Approved: | Ing. Zuzana Jonáček |  |  |
| Approved by the MoE | Ing. Zuzana Kocunová |  |  |